Bootcamp

UI/UX, Web Development, Backend Development and Flutter

Unpaid

6 months

Remote

We are offering bootcamp to IT students and professionals. They will learn, perform and gain the real practical experience in internships.

How to manage them from day one to last day without having them feel that they are doing a job in a company instead of internship? But yet they are learning from building the company's project in their internships.

Got it ✅ — you want to run a 6-month remote bootcamp that feels like a guided learning experience (not like a job), but still lets interns build real company projects.

The key is to design the program like a structured bootcamp + mentorship journey, where the primary focus is learning and real project work is the medium of teaching.

# 🎯 Bootcamp Management Framework (Day 1 → Last Day)

## 1️⃣ Orientation & Foundation (Week 1–2)

- Welcome Session: Explain it’s a bootcamp, not a job → they’re here to learn by building.

- Roadmap Document: Give them a syllabus (modules + tools + expected outcomes).

- Mentor Assignment: Pair each student with a senior (weekly guidance calls).

- Tools & Setup: GitHub, Figma, Jira/Trello, Slack/Discord → teach usage.

✅ Outcome: Everyone is set up, knows the journey, and feels like part of a learning group.

## 2️⃣ Guided Learning Phase (Month 1–2)

- Weekly Workshops (recorded + live Q&A):

  - UI/UX → Design systems, wireframes.

  - Web Dev → HTML, CSS, JS basics → small components.

  - Backend → REST APIs, DB basics → simple CRUD.

  - Flutter → UI widgets, state mgmt basics.

- Mini Projects (not real company yet):

  - Clone a landing page.

  - Build a simple “todo API”.

  - Flutter login screen.

✅ Outcome: They practice skills in safe projects → feel like learners, not workers.

## 3️⃣ Real Project Contribution (Month 3–4)

- Start integrating them into real company projects BUT with a learning-first angle.

- Break projects into intern-level tickets (not mission-critical tasks).

- Process:

  - Mentor explains task (why + how).

  - Intern implements.

  - Mentor reviews code/design → gives feedback.

- Bi-weekly Check-ins: Group discussion on what they learned.

✅ Outcome: They apply skills to “real stuff” but framed as learning-by-doing, not “delivering for the company”.

## 4️⃣ Independent Feature Ownership (Month 5)

- Assign each intern a mini-project/feature to build end-to-end. Examples:

  - UI/UX: Redesign a signup flow.

  - Web Dev: Build a reusable component library.

  - Backend: Create a reporting microservice.

  - Flutter: Add notifications feature.

- Encourage cross-track collaboration (UI/UX + Dev + Backend + Flutter interns working together).

✅ Outcome: They feel confident, take ownership, and showcase applied learning.

## 5️⃣ Showcase & Graduation (Month 6)

- Final Demo Day: Interns present what they built (recorded presentations + portfolio links).

- Feedback Session: Share mentor feedback + improvement areas.

- Certificates & Recommendations: Highlight skills gained + projects completed.

- Portfolio Support: Help them push work to GitHub, Behance, LinkedIn.

✅ Outcome: They graduate with practical experience + a portfolio, not just “time spent”.

# 💡 Tips to Keep It “Bootcamp Vibe”, Not “Job Vibe”

- Frame work as challenges, not “deliverables”. (“You’ll learn how to implement a login flow” → not “We need this by tomorrow”).

- Always mentor-review → learning through feedback.

- Gamify → badges, certificates for milestones.

- Community-first → Slack discussions, peer reviews, shared learning.

- Flexibility → since unpaid/remote, keep flexible hours but fixed checkpoints.

- Celebrate wins → shoutouts, leaderboard, “Intern of the Month”.

✅ This way, interns:

- Don’t feel like employees.

- Get structured learning + real-world exposure.

- Leave with skills, confidence, and portfolio projects.

Would you like me to create a week-by-week bootcamp roadmap (24 weeks) that you can directly hand to interns as their official learning journey?